## Sheet1
LockerMe Agile Project Plan
Task Name | Priority | Owner | Start Date | End Date | Status
Sprint #1: Analysis and Design
Making Sprint Plan | High | Pravallika | 2022-03-21 | 2002-03-29 | In Progress
Specification document | Low | Pravallika | 2022-03-22 | 2002-03-24 | Not Started
Prepare Algorithm | High | Pravallika | 2022-03-23 | 2002-03-25 | Not Started
Create Flow Chart | Medium | Pravallika | 2022-03-24 | 2002-03-25 | Not Started
Setup Git Repository | High | Pravallika | 2022-03-21 | 2002-03-22 | Done
Sprint #2: Develop and Execute
Code to display the welcome screen and Main Menu | Medium | Pravallika | 2022-03-28 | 2002-03-30 | Not Started
Code to add file | High | Pravallika | 2022-03-28 | 2002-03-30 | Not Started
Code to delete file | High | Pravallika | 2022-03-29 | 2002-03-31 | Not Started
Code to search file | High | Pravallika | 2022-03-29 | 2002-04-01 | Not Started
Code to Navigate and close Application | Medium | Pravallika | 2022-03-31 | 2002-04-01 | Not Started
Sprint #3: Test, Fix & Install
Test the Application | High | Pravallika | 2022-03-04 | 2002-04-05 | Not Started
Fix issues | High | Pravallika | 2022-03-05 | 2002-04-06 | Not Started
Retest Application | Low | Pravallika | 2022-03-05 | 2002-04-06 | Not Started
Upload to Git Repository | Medium | Pravallika | 2022-03-05 | 2002-04-06 | Not Started
Submit Project | High | Pravallika | 2022-03-05 | 2002-04-06 | Not Started